# **Non-Government Reform Support Fund**

# **2022 Workplan**

# **Queensland Catholic Education Commission**

## **Non – Government Reform Support Fund**

## **Queensland Catholic Education Commission – Workplan 2022**

### **Summary of Workplan for 2022**

The Queensland Catholic Education Commission (QCEC) 2022 Work Plan for the Non-Government Reform Support Fund (NGRSF) is based on the reform priorities as identified in the 2022 NGRSF Guidelines which are:

1. Support the implementation of the eight national policy initiatives set out at clause 44 of the National School Reform Agreement
2. Continue to track and monitor the education outcomes of students in the schools they represent consistent with clause 37 of the National School Reform Agreement, including
   1. National Assessment Program – Literacy and Numeracy (NAPLAN) outcomes for Years 3, 5, 7 and 9; and
   2. Organisation for Economic Cooperation and Development’s (OECD) Programme for International Student Assessment (PISA) testing in reading, mathematics and science.
3. Implement state-based reform actions in the bilateral reform agreement, including
   1. Support students and student learning
   2. Support teaching, school leadership and school improvement
   3. Enhance the national evidence base
4. Strengthen the three national priorities; which are:
   1. Improve the quality of information on the Nationally Consistent Collection of Data on School Students with Disability, and to improve the efficiency and integrity of the data collection
   2. Transition of NAPLAN to online delivery
   3. Improve governance and financial management practices to strengthen financial viability, improve business decision making and build resilience to mitigate unforeseen circumstances
5. Local priorities aligned with the Quality Schools agenda.

QCEC is committed to ensuring that NGRSF funds are used to maximise outcomes against the agreed national and bilateral initiatives for Catholic schools in Queensland. An overarching Summary of Budget for all projects across QCEC and Catholic School Authorities has been provided.

**Structure of the Queensland Catholic Education Commissions and Catholic School Authorities**

QCEC is the peak body representing Catholic education in Queensland. QCEC works with the five diocesan Catholic School Authorities (CSAs) and 17 Religious Institutes (RI) and Public Juridic Persons (PJPs) School Authorities. In 2022, there are 309 Catholic schools in Queensland, run by 22 Catholic School Authorities (i.e QCEC does not own or operate any of the 309 Catholic schools).

In 2022 activities to progress significant National and State reform priorities and meet obligations under the bilateral agreement will be managed both centrally by QCEC, as well locally by CSAs to ensure they best meet the local context. Both centrally administered activities and local activities are identified in the following workplans.

The diagram of the flow of information, assistance and funding between QCEC and the CSAs has been provided below:

**Diagram

Description automatically generated**

**Diagram

Description automatically generated**

### **Summary Budget**

| **CSA** | **Project** | **Activities** | **Reform**  **Support funding** | **Funding from other sources** | **Total project funding** |
| --- | --- | --- | --- | --- | --- |
| QCEC | **NCCD** | Training, professional learning and moderation sessions to improve collection of data to support the NCCD | $145,000 | $0 | $145,000 |
| QCEC | **NAPLAN** | Support for the transition of all Queensland Catholic schools to NAPLAN Online delivery | $122,000 | $0 | $122,000 |
| QCEC | **HALT** | Manage and lead processes to support the certification of aspiring Highly Accomplished and Lead Teachers  Provide support for the assessment and moderation of portfolios through assessor training and moderation activities  Provide online support to HALT applicants through customised modules and resources on a customised website | $232,395 | $0 | $232,395 |
| QCEC | **SATE** | Support for the delivery of the new Queensland Certificate of Education (QCE) system through professional learning events. | $5,000 | $0 | $5,000 |
| BCE | **NCCD** | Support for the Nationally Consistent Collection of Data on Students with Disabilities | $600,000 | $0 | $600,000 |
| BCE | **Early Years Screening Tools** | Accelerate in the Early Years: Early Years Partnership | $600,000 | $0 | $600,000 |
| BCE | **Support Rural Wellbeing** | Wellbeing in Rural Schools | $170,000 | $0 | $170,000 |
| BCE | **Parent, community, and industry engagement** | Improving career readiness of BCE graduates | $241,000 | $0 | $241,000 |
| BCE | **Data Literacy / School Improvement** | Data literacy for school leaders | $85,000 | $0 | $85,000 |
| BCE | **School Improvement and HealthCheck** | Develop and launch new School Improvement and HealthCheck with professional engagement of senior Principals as Review Panel Chairs | $315,782 | $0 | $315,782 |
| RIPJP | **NCCD** | Support for RI/PJP and EREA schools in the NCCD through the provision of TRS and an Inclusive Education Consultant and their assistant. | $215,000 | $0 | $215,000 |
| RIPJP | **HALT** | Support for staff in RI/PJP and EREA schools looking to achieve Highly Accomplished or Lead Teacher certification through the engagement of a HALT Facilitator. | $137,500 | $0 | $137,500 |
| RIPJP | **Leadership Development** | Delivery of the *Leading with Integrity and Excellence* program for Principals and Aspiring Principals in RI/PJP and EREA schools. | $165,150 | $0 | $165,150 |
| RIPJP | **Student Engagement** | Purchase user licences for the PIVOT engagement tool | $37,500 | $0 | $37,500 |
| RIPJP | **School Improvement - School Reviews** | Support school improvement through the provision of training on the National School Improvement Tool and the subsidisation of ACER School Reviews. | $217,575 | $0 | $217,575 |
| RCEO | **NCCD** | TRS, travel, accommodation and catering for professional development phases of the NCCD. | $198,000 | $0 | $198,000 |
| RCEO | **Existing and aspiring school leaders** | The provision of three courses offered through QELi including Professional and Difficult Conversations, Middle Leaders Course and Teach Like a Champion Course. | $100,725 |  |  |
| RCEO | **Existing and aspiring school leaders** | Leading Mathematics Education | $33,247 | $0 | $133,972 |
| RCEO | **Student Wellbeing** | Royal Far West counselling support for students in Blackall, Longreach, Barcaldine, Springsure, Clearmont, Biloela and Monto | $122,320 | $0 | $122,320 |
| TNS | **Student Wellbeing** | LOVE BiTES Respectful Relationships Program | $16,000 | $0 | $16,000 |
| TNS | **Early Years** | Support Early Years Teachers’ implementation of pre and post testing for literacy and numeracy | $81,512 | $43,488 | $125,000 |
| TNS | **HAT / LT Certification** | Support teachers’ participation in Highly Accomplished and Lead Teacher certification processes | $25,000 | $0 | $25,000 |
| TNS | **PIVOT** | Teachers in our secondary schools will engage in the PIVOT student voice surveys | $25,000 | $0 | $25,000 |
| TNS | **Leadership Development** | ‘Leading from Within’ Middle Leaders’ Program | $40,000 | $0 | $40,000 |
| TNS | **Leadership Development** | Aspirant Leaders’ Program (Western Region) | $35,000 | $0 | $35,000 |
| TNS | **Leadership Development** | 7 Habits of Highly Effective Leaders Program | $35,000 | $0 | $35,000 |
| TNS | **SMART IE Data** | School Motivation and Response To Indigenous Education (SMART IE) Data Project | $80,000 | $0 | $80,000 |
| CCE | **NCCD** | Support for local projects and engagement in QCEC Central projects to support the Nationally Consistent Collection of Data on Students with Disability. | $106,000 | $0 | $106,000 |
| CCE | **Clarity – An approach to system-wide school improvement.** | A program to support schools to focus on the 14 parameters of System and School Improvement as outlined in the text by Sharratt, *Clarity – What Matters Most in Learning, Teaching and Leading.* | $200,530 | $80,000 | $280,530 |
| TOO | **NCCD** | Toowoomba Catholic Schools Office and school staff will participate in the QCEC NCCD project activities, including training, moderation and reflection regarding the NCCD to upskill teachers and leadership on processes for continued improvement of NCCD.  Office staff will continue to work with school staff to increase capacity and knowledge and work towards consistency of judgement. | $20,000 | $20,000 | $40,000 |
| TOO | **Digital and data literacy** | In-services and support to schools in developing data literacy and data planning capabilities in schools. | $47,139 | $1,000 | $48,139 |
| TOO | **Leadership learning program – Middle leaders** | Services across primary and secondary year levels with associated expenses including TRS, travel, catering, accommodation costs, resources across the year.  Engage and develop familiarity with key systems, strategic documents and expectations including TCS leadership.  Facilitate ongoing networking and collaboration between middle leaders and established system and school leaders | $29,000 | $0 | $29,000 |
| TOO | **Leadership learning program - Deputisers** | In-services across primary and secondary year levels with associated expenses including TRS, travel, catering, accommodation costs, resources across the year.  Ensure sufficient knowledge of and familiarity with key responsibilities associated with the deputiser’s role.  Engage and develop familiarity with the Toowoomba Catholic Schools Leadership Framework and capabilities.  Facilitate ongoing networking and collaboration between deputisers and established school and system leaders. | $25,000 | $0 | $25,000 |
| TOO | **School review and improvement processes** | Implementation of the program within the school environment with costs including TRS for staff involved from within the school and other schools, consultancy fees, travel and accommodation costs.  Support the work of school leaders, staff, students and community in evaluating the effectiveness of programs and directions against agreed goals and priorities.  Develop capabilities and practices associated with effective strategic planning and decision making.  Ensure local and system accountability to school communities and the government for the prudent oversight of resources and staffing to attain the desired student outcomes. | $72,000 | $0 | $72,000 |
| TOO | **Peoplebench Project** | Engagement costs for Peoplebench organisation for 2022.  Utilise predictive analytics to assist leaders to make data-driven predictions based on behaviour and trends.  Enhance the capacity of principals and other system leaders to effectively utilise this data to inform strategic planning and decision-making. | $48,825 | $0 | $48,825 |
| QCEC | **Administration** | NGRSF Administration Costs | $45,000 | $0 | $45,000 |
|  |  | **TOTAL FUNDING** | **$4,674,200** | **$144,488** | **$4,818,688** |

# **Non-Government Reform Support Fund**

# **2022 Workplan**

# **Queensland Catholic Education Commission Central Fund**

### **Summary of Budget – Queensland Catholic Education Commission Workplan 2022**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project** | **Activities** | **Reform Support Funding** | **Funding from other sources** | **Total project funding** |
| **NCCD** | Training and professional learning and moderation sessions to improve collection of data to support the NCCD | $145,000 | $0 | $145,000 |
| **NAPLAN** | Support for the transition of all Queensland Catholic schools to NAPLAN Online delivery | $122,000 | $0 | $122,000 |
| **HALT** | Manage and lead processes to support the certification of aspiring Highly Accomplished and Lead Teachers  Provide support for the assessment and moderation of portfolios through assessor training and moderation activities  Provide online support to HALT applicants through customised modules and resources on a customised website |  |  |  |
| **SATE** | Support the delivery of the Queensland Certificate of Education (QCE) system through professional learning event/s for teachers | $5,000 | $0 | $5,000 |
| **Administration** | NGRSF Administration costs | $45,000 | $0 | $45,000 |
|  | **Total Funding** | **$549,395** | **$0** | **$549,395** |

## **Non-Government Reform Support Fund**

### **Queensland Catholic Education Commission Central Fund Workplan 2022**

| **Project Title** | **Project Description and Activities** | **Indicative Budget** | **Expected Outcomes/Overall Achievements** | **Indicators of Success** |
| --- | --- | --- | --- | --- |
| 1. **Nationally Consistent Collection of Data on Students with Disability**   National Policy initiative: Reform Direction C – Enhancing the national evidence base  Reform Support Fund priority: Nationally Consistent Collection of Data on School Students with Disability | This project will deliver professional development activities to continue to improve the consistency of Catholic education staff’s understanding of the NCCD and through doing so, improve on the collection of evidence of adjustments and reporting of data about school students with disability. Activities will focus around the key areas of training about the NCCD model, cross-school and/or cross-sector moderation and NCCD reflection and planning.  Staff will be supported to participate in training and cross-school and/or cross-sector moderation processes for their students, to assist with strengthening their knowledge and understanding of the NCCD processes and to assist them to engage with quality assurance processes.  Work at diocesan level with key staff from Catholic School Authorities will continue to build sustainable practices in professional learning, moderation, and quality assurance.  **Overview of planned 2022 NCCD activities**:  **NCCD Training – 9** programs (F2F and online)  **NCCD Leading Practice** – 17 sessions  **NCCD Moderation**  Cross-school moderation within Queensland Catholic schools – 30 sessions (F2F and online)  Cross-sector moderation – 10 sessions (as per the Bilateral Agreement).  **NCCD preliminary anomaly check and feedback** offered to all Queensland Catholic schools  **NCCD Reflection and Planning** – 24 sessions | $145,000  FTE: 1.0 Staff | * Professional development/learning is provided about the NCCD through training, moderation, and reflection activities * Classroom/subject teachers are encouraged to attend NCCD training about the model and cross-school moderation sessions, to increase their confidence around planning, recording, and monitoring educational adjustments | * School-based decisions about the level of adjustment and category of disability are endorsed through cross-sector moderation * There is a reduction in the number of queries from the Australian Government Department of Education * Catholic school staff experience increased confidence in the accuracy of the school level data submitted for census * Participants report a higher level of confidence around planning, recording, and monitoring educational adjustments for students with disability |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project Title** | **Project Description and Activities** | **Indicative Budget** | **Expected Outcomes/Overall Achievements** | **Indicators of Success** |
| 1. **NAPLAN Online Coordination Project**   National Policy Initiative:Reform Direction C – Enhancing the national evidence base  Bilateral Agreement Action: Data literacy and development (support rollout of NAPLAN Online to Catholic schools) | With the remainder of Queensland Catholic schools expected to transition to NAPLAN Online in 2022, this project will support the remaining transitioning schools in the areas of sector-wide training to Catholic school staff in conjunction with test administration authority, support for in-school training of test administrators, and support for 2022 online testing.  The following events will be held:   * Refresher (national protocols) training * In-school training of Test Administrators * School readiness preparation activities and practice testing   Additionally, this project will support schools and authorities in accessing NAPLAN data including advice on Student and School Summary Reports.  Pending Covid-19 restrictions, the event/s associated with this project will be held online. | $122,000  FTE: 1 staff | * Schools are supported to complete the transition to NAPLAN Online * Delivery of in-school test administration training, school readiness preparations and practice testing. * Schools/authorities are supported to access and use NAPLAN data and reports to gain insights into student progress | * 100% of Catholic schools are ready for NAPLAN online testing in May 2022 * All schools transitioning to NAPLAN Online in 2022 attend refresher (national protocols) training in January-March 2022 * Schools participate in school test administration training, school readiness preparations and practice testing in March – April 2022 prior to NAPLAN testing in 2022 * Schools have increased confidence in using data from the Student and School Summary Reports when released in August 2022 to inform school directions to support students |

| **Project Title** | **Project Description and Activities** | **Indicative Budget** | **Expected Outcomes/Overall Achievements** | **Indicators of Success** |
| --- | --- | --- | --- | --- |
| 1. **Highly Accomplished and Lead Teacher Initiative**   National Policy Initiative: Reform Direction B - Support teaching, school leadership and school improvement  Bilateral Agreement Action: Highly accomplished and lead teachers | This project will continue to recognise the explicit value of teaching experience and proven ability in the classroom by rewarding highly accomplished and lead teachers (HAT LT) through the following activities:   * The provision of specific support for Catholic school leaders so they can support HAT LT applicants. * The continuation of the HAT LT assessors’ network. * The training of additional HAT LT assessors, including refresher training of HAT LT assessors. * Information sessions and in-depth workshops scheduled prior to applicants submitting their Notification of Intention to Apply for Certification. * Reimbursement to Queensland College of Teachers (QCT) (Client fee) for providing services to support QCEC Certification processes including: Initial Assessor Training, Assessor Refresher Training, Introductory Sessions, In-Depth Workshops, Client Application fees, and potential Internal Review Committee (IRC) fees (appeals cost). * Support access to customised online modules to assist applicants in the development of HAT LT portfolios with a specific Catholic lens. * Support trained Facilitators to deliver professional learning opportunities (Introductory Sessions and In-Depth Workshops) within all Queensland Catholic Dioceses and for all Catholic School Authorities. * Continue to work with the QCT in renewal of certification work * Support AITSL initiatives including HALT Summit | $232,395  FTE: 0.6 staff | * More Queensland Catholic school teachers apply for HAT LT certification. * Certification renewal is communicated and supported with QCEC resources. * HAT LT Applicants and Aspiring HAT LT Applicants are supported through the provision of   + Increased support and the promotion of certification from school leaders   + Professional Learning opportunities, including Introductory and In-Depth Workshops * Online Learning Module development is finalised, released and maintained for engagement by aspiring teachers and school leaders * Teachers have access to resources on an updated website which support the HAT LT application process. * HALT Assessment processes are strengthened to support the fidelity of assessment processes through the provision of   + HAT LT assessor training   + Support for assessment and moderation activities   + Communication regarding refresher training. | * In 2022 more than 14 teachers will apply for HAT LT status in Queensland Catholic schools representing an increase in the number of applicants from 2021. * 2022 HAT LT Applicants report experiencing support from their school leaders and trained Diocesan Facilitators. * Increased engagement in the Introductory Sessions and In-Depth Workshops indicated in attendance rates. * Multiple opportunities for professional development increase the knowledge of certification, indicated through session and workshop attendance surveys * Website updates will incorporate certification renewal resources developed for QCEC. * Increased engagement with HAT LT communications via newsletters, online modules and website, indicated through Vison 6 monitoring for opening rate and deep engagement data. * In 2022, 14 or more Assessors will be trained to support Catholic Schools representing an equivalent or higher number of assessors trained compared to 2021 and an overall increase in the total number of Catholic School trained and current HAT LT assessors. |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project Title** | **Project Description and Activities** | **Indicative Budget** | **Expected Outcomes/Overall Achievements** | **Indicators of Success** |
| 1. **SATE**   National Policy Initiative: Reform Direction A – Support students and student learning  Bilateral Agreement Action: Senior Assessment and Tertiary Entrance reform | This reform support project will continue to provide support to Queensland Catholic school leaders and teachers with the ongoing implementation of Queensland’s senior assessment and tertiary entrance system (SATE).  This activity will provide senior secondary teachers an opportunity to network in subject-area groups, share learnings and resources from their first years of teaching the new syllabus, and improve their practice in supporting students prepare for External Assessments. Keynote speakers from the QCAA will be invited to present in three professional development sessions, focused on areas of the new SATE system including Applied Syllabuses, External Assessment preparation and Access Arrangements and Reasonable Adjustments (AARA).  Pending Covid-19 restrictions, the event/s will be held in a blended or online mode. | $5,000  0 FTE | * Three cross-authority events hosted to support senior secondary teachers refine their practice in the new SATE system. * Increased confidence of Catholic school staff in Catholic School Authorities and RI/PJP schools in relation to the requirements of the Queensland Certificate of Education (QCE) system | * More than 60% of participating teachers surveyed after the events report an increase in confidence and capability teaching and assessing the new senior secondary syllabus. |

# **Non-Government Reform Support Fund**

# **2022 Workplan**

# **Brisbane Catholic Education**

## **Summary of Budget – Brisbane Catholic Education**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project** | **Activities** | **2022**  **Reform support funding** | **Funding from other sources** | **2022 Total project funding** |
| **NCCD** | NCCD | $600,000 | $0 | $600,000 |
| **Early Years Screening**  **Tools** | Accelerate in the Early Years: Early Years Partnership | $600,000 | $0 | $600,000 |
| **Support Rural Wellbeing** | Wellbeing in Rural Schools | $170,000 | $0 | $170,000 |
| **Parent, community, and industry**  **engagement** | Improving career readiness of BCE graduates | $241,000 | $0 | $241,000 |
| **Data Literacy / School Improvement** | Data literacy for school leaders | $85,000 | $0 | $85,000 |
| **School Improvement and HealthCheck** | Develop and launch new School Improvement and HealthCheck with professional engagement of senior Principals as Review Panel Chairs | $315,782 | $0 | $315,782 |
|  | **Total funding for 2022** | **$2,011,782** | **$0** | **$2,011,782** |

\* The Australian Government understands that these figures provided are indicative and may change throughout the year. The Annual Report will report on any changes.

## **Non-Government Reform Support Fund**

### **Brisbane Catholic Education Workplan 2022**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project title** | **Project description and activities** | **Indicative budget** | **Expected Outcomes/ Overall achievements** | **Indicators of success** |
| 1. **Project title: NCCD**   National Policy initiative: Reform Direction C – Enhancing the national evidence base  Reform Support Fund priority 7(a): Quality assurance, moderation and support for the continued improvement of the Nationally Consistent Collection of Data on School Students  with Disability | Project led by BCE personnel to strengthen quality assurance, moderation, and support for the continued improvement of the Nationally Consistent Collection of Data for students with disability.  Key focus areas:   * in-school moderation activities * individual schools’ completion of NCCD Reflection Tool and forward planning for next cycle   Complemented by:  QCEC personnel led activity to strengthen quality assurance, moderation, and support for the continued improvement of the Nationally Consistent Collection of Data for students with disability.  Key focus areas:   * Information sessions for new staff * Cross-school moderation sessions * Cross-sector moderation sessions. * Internal school moderation sessions. | **Reform support funding:**  $600,000  Other funding: $0  FTE: 1.0 Project Officer $132,000  Teacher Release:  $468,000 | * Decisions regarding levels of adjustment and disability category are identified as accurate through in-school moderation process. * Goals are identified for improvement in the next cycle of NCCD. * Improved confidence in decision-making by BCE quality assurers. * Alignment of decisions regarding levels of adjustment and disability category between schools and sectors. | * Quality assurance process confirms the accuracy of school decisions. * BCE NCCD data indicates alignment with other dioceses, sectors, state-wide and nationally. * Limited changes during quality assurance process after submission of preliminary data. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/ Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| **2. Accelerate in the Early Years**  **– Early Learning Partnerships**  National Policy Initiative: Reform Direction A – Support students and student learning  Bilateral Agreement Action: Review and extend early years screening tools in Qld Catholic schools | This project will lead to an established and informed response to scale across various school contexts through the identification of early screening tools, partnerships, practices, processes and structures that sit within and around the Levels of Teaching Response as a framework to inform decision making that best responds to student early literacy growth and progress.  This project extends Brisbane Catholic Education’s (BCE) current focus on effective and expected leadership and teaching practices to identify and implement processes and practices that ensure each student receives the responsive teaching they require, when and as they need it.  This project is led by BCE and runs from 2020-2022. In this final phase, this project will further develop and articulate school-based partnerships, processes and practices that respond to student learning progress and provide responsive teaching and support, that results in learning progress and achievement for every student. | Reform support funding: $600,000  Other funding: $0  Staffing: $360,000  2.0 FTE Project Officers (Educators)  and  0.4 FTE Speech Pathologist  Teacher Release: $240,000 | * Building of each role holders' capacity (teachers, Primary Learning Leaders, Support Teachers, Leadership teams and other specialists) to best respond to each student’s learning progress in a timely way. * Participants report a deeper understanding of Partnerships, practices, processes and structures that need to exist in schools to progress the learning of each student including the pivotal contribution of speech pathology. * A refined understanding of how the Levels of Teaching Response can be used as a framework to progress the learning of each student. * A review and deepened understanding of Early Years Screening tools that can be upscaled and shared, to provide our schools with the right information at the right time to inform a response to move early literacy acquisition and the associated literacy skill development forward to impact progress for each student. | * Schools report an increase in responsive teaching and differentiating resulting in increased numbers of students achieving 95% using PM Reading Benchmarks tool. * Early literacy progress monitored through Letter/Sound knowledge, Concepts of Print and PM benchmarking will provide quantifiable measures of success. * Levels of Teaching Response process is refined, elaborated and exemplified. * Models/examples of effective practice are used to scale up implementation across 35 additional schools in 2022. |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Project title** | **Project description and activities** | | **Indicative budget** | | **Expected outcomes/ Overall achievements** | | **Indicators of success** |
| **3. Project Title: Wellbeing in Rural Schools**  National Policy Initiative: Reform Direction B – Support teaching, school leadership and school improvement  Bilateral Agreement Action: Rural and remote wellbeing | The Brisbane Catholic Education (BCE) Strategic Plan (2021-2025) identifies *Wellbeing* as a priority. Current educational research highlights the alignment between deep learning with improved student wellbeing. Increasingly, rural communities are required to draw upon their school, Parish and local communities to support the wellbeing and mental health of their students.  This project, extended to a second year after a successful initial year, is being implemented in the contexts of BCE North & South Burnett, Wide Bay, Maryborough and Gympie schools. It aims to build the capacity of staff in developing prevention and early intervention responses in promoting positive student wellbeing and understanding the Levels of Teacher Response in deepening learning. | | Reform support funding: $170,000  Other funding: $0  FTE: 1.0 FTE staff  Rural Engagement Support Coordinator salary, travel and office costs $150,000  Teacher Release Funds for professional development sessions: $20,000 | | * Key personnel of each school (Leadership Team Representative, Guidance Counsellor, Support Teacher Inclusive Education, Primary and Secondary Learning Leaders) engage in the project. * Schools review support structures naming and implementing prevention and early intervention strategies related to student wellbeing and learning engagement. * Schools initiate programs and activities that inextricably link student wellbeing and learning. * Partnerships between school and identified local wellbeing support agencies, and collaboration between schools in the project developed. * Support schools in developing Levels of Teacher Response in their staff. | | * Project engagement by at least 80% Brisbane Catholic Education schools in the North & South Burnett, Wide Bay, Maryborough and Gympie regions. * 100% of schools document evidence of intervention strategies to support student engagement in the Engage Student Support System * Initiate programs/activities recorded in implementation documents/teacher planning * Of the schools who engage in professional learning for Levels of Teaching Response, 100% have attendance by a School Lead and one other staff member as shown in attendance lists. |
| **Project** | | **Project description and activities** | | **Indicative budget** | | **Expected outcomes/ Overall achievements** | | **Indicators of success** |
| **4. Project Title: Improving the career readiness of BCE graduates**  National Policy Initiative: Reform Direction B – Support teaching, school leadership and school improvement  Bilateral Agreement Action: Provide Professional learning  opportunities and resources to enhance parent, community, and industry engagement with  Catholic schools | | Local Project led by Brisbane Catholic Education (BCE) to conduct an extensive review of secondary structures and practices to evaluate and improve the way in which BCE schools prepare students for successful global citizenship, regardless of their choice of pathway. The review, conducted across 2021, will be used to inform improved Career Readiness activities in schools from 2022.  The review has resulted in an action plan and supporting resources to ensure students’ learning is integrated and authentic, enhances the skills necessary for successful citizenship and provides a research-informed framework for careers education.  This final phase of the project will result in a broader range of schools using the outcomes of the review to implement enhanced processes in preparing students for life after school. | | Reform support funding:  $241,000  Other funding: $0 FTE:1.6 FTE staff  0.6 FTE Project Officer: Contemporary learning focussing on pedagogies for career skill development as well as careers education:  $88,000  1.0 FTE Project Officer: Online Learning focussing on broadening senior pathway options for students, regardless of school size, location, or context: $153,000 | | * Improved student engagement and wellbeing outcomes (including improved attendance data for schools engaged in the pilot phase). * Improved student pathway options achieved through renewed parent, community, and industry engagement (resulting in a decrease in student attrition in the senior phase of learning). * Improved student understanding of career options (resulting in engagement with careers aligning with personal strengths and interests, rather than being limited to the career information provided by parents or significant others). * Improved development of students’ skills for success in the workforce (regardless of pathway). | | * Implementable recommendations/framework for the future improvement of career readiness for BCE graduates. * The first phase of a Catholic school of distance education is launched for senior students for 2022 (to allow for a greater breadth of subject offerings for all students). * Refinement of support resources (including professional learning) and community and industry engagement to assist with change processes required for greater career readiness. * Career readiness program implemented with defined cohort of schools which have demonstrated readiness for participation. |
| **Project title** | | | **Project description and activities** | **Indicative budget** | **Expected outcomes/ Overall achievements** | | **Indicators of success** | |
| **5. Project Title: Data literacy for school leaders**  National Policy Initiative: Reform Direction C – Enhancing the national evidence base  Bilateral Agreement Action:  Develop strategies to enhance data literacy among Catholic school leaders and teachers, support the dev of data tools and frameworks to inform planning and development of educational policy and practices in Catholic schools | | | Local Project lead by Brisbane Catholic Education (BCE)  Program will continue to focus on NAPLAN error analysis and Australian Curriculum Literacy and Numeracy requirements, with further refinement of BCE dashboards and reports relevant to key stakeholders in the BCE office and schools.  Additional data analytics development required to build and enhance the HealthCheck platform and termly data updates to support system data priorities  Products and resources previously developed will be used across BCE schools and office leaders and teachers.  Continue to build data literacy capacity of system and school leaders in the application and analysis of data to strategically drive System and School priorities leading to improved system learning performance. | Reform support funding  $85,000  Other funding: $0  FTE: 0.5 FTE staff  0.5 FTE Project Officer  $85,000 | * School leadership teams increase use of data to inform decision making and strategic planning. * System leaders use data evidence base to drive system improvement and performance. * Understanding and effective implementation of processes and practices to analyse school datasets and identify key themes for strategic action that results in school improvement. * Focussed analysis of NAPLAN data to inform future teaching emphasis across BCE schools. * Provide digital platform which includes low level data security for all BCE School Principals and leadership teams and system leaders access to the PowerBI app/PowerApp called the ‘HealthCheck’ | | * Leaders report greater understanding of how to establish positive environments for data conversations * Improved documentation of strategic goals and annual plans with evidence of data informed decision making * Targeted and precise allocation of resources to support strategic intents. * All schools Principals, Leadership teams and System Leaders have access to the PowerBI HealthCheck app and are engaging with the HealthCheck PowerBI/ PowerApp to track school key performance indicators | |
| **Project title** | | | **Project description and activities** | **Indicative budget** | **Expected outcomes/ Overall achievements** | | **Indicators of success** | | |
| **6. Project Title:**  **School Improvement and Health Check**  National Policy Initiative: Reform Direction B – School Improvement and School Leadership:  Enhance school improvement processes and planning with Catholic schools  and  Support school leadership and school improvement through initiatives aimed at enhancing strategic leadership for existing… school leaders… | | | The Brisbane Catholic Education (BCE) Strategic Plan (2021-2025) identifies the need to design a new school improvement framework that supports organisational priorities and to introduce a quarterly HealthCheck for each school.  This project will engage experienced Principals as Panel Chairs for multiple School Reviews as a means of developing their insight into quality schooling and school improvement issues. | Reform support funding: $315,782  Other funding: $0  Staff 2.0 FTE  Contribution to project costs including 4 senior Principals (Primary and Secondary for 1 Semester full-time) | * Launch a quarterly HealthCheck process for schools * Train Senior Leaders and Principals in HealthCheck processes and linkages to the improvement agenda of each school and the organisation. * Set each quarterly HealthCheck focus in response to emerging trends and needs and refine the process on basis of experience. * Use the previously developed BCE Curriculum Compliance Guide (P-12) * Refine the Curriculum Compliance Audits process introduced in some schools 40% of schools in 2021. * Introduction and use of a refined School Improvement Tool which draws upon School HealthCheck, Curriculum Compliance data and BCE Organisational Priorities. | | • HealthCheck data is available each term for every school. (n of schools greater than 95%)  • HealthCheck data is available for interrogation and analysis within the BI Tool for school and system leaders to inform future planning and improvement. (n of schools greater than 95%)  • Curriculum Compliance Audits identify the extent that schools are compliant with the curriculum and any risks areas.  • Curriculum Compliance Audits identify further improvement opportunities – name top three.  • Availability of a School Improvement tool which allows for incorporation of BCE priorities over time.  • Incorporation of School Improvement, Compliance and Health Check data in the BI Intelligence tool in support of future improvement actions | | |

# **Non-Government Reform Support Fund**

# **2022 Workplan**

# **RI/PJP Schools**

### **Summary of Budget – RI/PJP and EREA Schools**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project** | **Activities** | **Reform support funding** | **Funding from other sources** | **Total project funding** |
| **NCCD** | Support for RI/PJP and EREA schools in the NCCD through the provision of:   * TRS for staff to participate in centrally managed NCCD learning and moderation activities * an RI/PJP Inclusive Education Consultant and Assistant to work across schools to build the capacity of school staff in the collection of data for the NCCD | $215,000 | $0 | $215,000 |
| **HALT** | Support for staff in RI/PJP and EREA schools looking to achieve Highly Accomplished or Lead Teacher certification through the engagement of a HALT Facilitator. | $137,500 | $0 | $137,500 |
| **LEADERSHIP DEVELOPMENT** | Delivery of the *Leading with Integrity and Excellence* program for Principals and Aspiring Principals in RI/PJP and EREA schools. | $165,150 | $0 | $165,150 |
| **STUDENT ENGAGEMENT** | Purchase user licences for the PIVOT engagement tool | $37,500 | $0 | $37,500 |
| **SCHOOL IMPROVEMENT – SCHOOL REVIEWS** | Support school improvement through the provision of training on the National School Improvement Tool and the subsidisation of ACER School Reviews. | $217,575 | $0 | $217,575 |
|  | **Total funding for 2021** | **$772,725** | **$0** | **$772,725** |

\* The Australian Government understands that these figures provided are indicative and will change throughout the year. The Annual Report is expected to report on these changes.

## **Non-Government Reform Support Fund**

### **RI/PJP and EREA Schools’ Workplan 2022**

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Nationally Consistent Collection of Data on Students with Disability**   National Policy initiative: Reform Direction C – Enhancing the national evidence base  Reform Support Fund priority: Nationally Consistent Collection of Data on Students with Disability | This project supports RI/PJP and EREA school staff to engage in activities to support the Nationally Consistent Collection of Data on Students with Disability (NCCD) through   * in-school sessions, * sessions directed by the RI/PJP Inclusive Education Consultant, and * activities hosted by QCEC.   The NGRSF funds support the engagement of an Inclusive Education Consultant and assistant to work across RI/PJP and EREA school clusters to support school staff to improve engagement with the requirements of the NCCD. | Reform support funding: $215,000  Other funding: $0  FTE: 2.0 | * The RI/PJP Inclusive Education Consultant works across schools to facilitate school leaders, teachers and curriculum leaders to use NCCD resources and tools available to assist with personalised learning for students with disability. * Teachers and school leaders are supported to engage with QCEC-facilitated training, moderation and reflection sessions | * Engagement of RI/PJP school staff in the Disability Standards for Education eLearning modules and case studies on the NCCD portal * Teachers and curriculum leaders have a greater confidence and capacity to capture the four forms of evidence of NCCD (consultation and collaboration, assessed and identified needs, planning and adjustments, and monitoring and reviewing). * The RI/PJP Inclusive Education Consultant provides professional learning opportunities for RI/PJP and EREA schools about the NCCD. * Teachers and curriculum leaders engage in cross-school moderation practices * Teachers and school leaders attend QCEC facilitated training, moderation and reflection sessions |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **HALT**   **National Policy Initiative:** Reform  Direction B - Support teaching, school leadership and school improvement    **Bilateral Agreement Action:** Highly accomplished and lead teachers | This project provides support for staff in RI/PJP and EREA schools looking to achieve Highly Accomplished or Lead Teacher certification through the provision of a HALT Facilitator, who works across all schools to   * Raise the profile of HALT certification * Improve understanding of HALT certification processes * Assist schools to support teachers seeking certification. | Reform support funding: $137,500  Other funding: $0  FTE: 1.0 | * In-school projects are delivered to raise the profile and understanding of HAT and LT certification in RI/PJP and EREA schools * Professional Development opportunities are provided for school leaders and teachers around HAT and LT certification * Assessors and applicants are supported by the HALT Facilitator | * Improved understanding of the HAT and LT certification process in RI/PJP and EREA schools * Participants in professional development sessions report a greater understanding of the processes of HAT and LT certification * The HALT Facilitator works across all RI/PJP and EREA schools to provide support for HAT and LT applicants |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Leadership Development**   **Reform Support Fund Priority B:** Support teaching, school leadership and school improvement  **Bilateral Reform Direction:** School Leadership (support school leadership and school improvement through initiatives aimed at enhancing school leadership for existing and aspiring school leaders and for school boards) | This project provides the opportunity for Principals and aspiring Principals to engage in the *Leading with Integrity for Excellence* (LWIE) program. This training is designed to build capacity around strategic leadership, accountability, governance and performance; in order to be efficient and effective administrators and leaders of learning within their school context.  The program improves stewardship of resources, governance, ethical practices and decision making, strategic thinking and performance; and enhances confidence, effectiveness and competence in areas of governance.  The indicative budget for this project would support one cohort of approximately 30 including course fees, catering, venue hire, and other associated costs with the program. | Reform support funding: $165,150  Other funding: $0  FTE: n/a | * Support for approximately 30 Principals and aspiring Principals to complete the LWIE program | * More than 60% of participants report improved understanding of financial management, governance, ethical practices, decision making, strategic thinking and performance. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Student Engagement**   **National Policy Initiative:** Reform Direction B – Support teaching, school leadership and school improvement    **Bilateral Agreement Action:** School Improvement (enhance school improvement processes and planning in Catholic schools) | This project allows RI/PJP and EREA schools to engage with the Pivot Student Engagement Tool, which collects data on student perceptions and teaching effectiveness over time to  provide a line of sight between individual teachers, school leaders, school authorities and QCEC on the effectiveness of teacher practice and strategies for continual improvement.  This tool will enable teachers to receive direct feedback on the effectiveness of their teaching through student surveys, aligned with the AITSL Professional Standards for Teachers. The survey results are private to the individual teacher but available at an aggregate level for school and system leaders. A range of resources are also provided to assist teachers in how to unpack the results of the survey and continually improve the effectiveness of their teaching. | Reform support funding: $37,500  Other funding: $0  FTE: n/a | * Participating teachers receive a report from the survey conducted with their students informing them of strengths and areas for improvement in their teaching practice * A cluster report is prepared for QCEC outlining trends from the student perception survey data | * Teachers report improvement in their teaching practice due to a greater understanding of student perceptions * Participating school leaders have access to data on teacher effectiveness * School planning is informed by data from the student perception surveys |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **School Improvement – School Reviews**   **National Policy Initiative:** Reform Direction B – Supporting teaching, school leadership and school improvement  **Bilateral Agreement Action:** School Improvement (enhance school improvement processes and planning with Catholic schools) | This project will support RI/PJP and EREA schools to conduct School Reviews using the National School Improvement Tool (NSIT) designed by the Australian Council for Education Research (ACER).  Support will be provided through training to school personnel on the NSIT through a two-day course, and through the subsidisation of school reviews conducted by ACER. | Reform support funding: $217,575  Other funding: $0  FTE: n/a | * Multiple school leaders from schools engage with the two-day training to identify key areas for school improvement from the National School Improvement Tool * Schools are supported to undertake a School Review conducted by ACER | * Participants report an increased understanding of using the National School Improvement Tool to support school improvement processes * School Reviews result in participating schools receiving a report providing detailed, evidence-based feedback in relation to the nine domains of the NSIT, as well as a set of overall commendations, affirmations and recommendations for school improvement. |

# **Non-Government Reform Support Fund**

# **2022 Workplan**

# **Catholic Education Diocese of Rockhampton**

### **Summary of Budget – Catholic Education Diocese of Rockhampton**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project** | **Activities** | **Reform support funding** | **Funding from other sources** | **Total project funding** |
| **NCCD** | TRS, travel, accommodation, catering for professional development phases of the NCCD:   * Training * Moderation (within and across schools) * Reflection | $198,000 | $0 | $198,000 |
| **EXISTING & ASPIRING SCHOOL LEADERS** | Three courses offered through QELi:   * Professional and Difficult conversations * Middle Leaders course * Teach like a Champion course | $100,725 | $0 | $133,972 |
| **EXISTING & ASPIRING SCHOOL LEADERS** | Leading Mathematics Education | $33,247 | $0 | $133,972 |
| **STUDENT WELLBEING** | Royal Far West counselling support for students in Blackall, Longreach, Barcaldine, Springsure, Clermont, Biloela, Monto | $122,320 | $0 | $122,320 |
|  | **Total funding for 2022** | **$454,292** | **$0** | **$454,292** |

## **Non-Government Reform Support Fund**

### **Catholic Education Diocese of Rockhampton Workplan 2022**

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **NCCD**   Reform Support Fund Priority 7(a): Quality assurance, moderation and support for the continued improvement of the Nationally Consistent Collection of Data on School Students with Disability  Bilateral Reform Direction C: Enhancing the national evidence base | ***Training:*** one day course to build understanding of NCCD purpose, processes and systems  ***Within school moderation:*** time for teachers to collaborate to review folios, work towards consistency of judgement; one day per stream per school for within-school moderation  ***Across-school moderation:*** moderation of evidence folios to build consistent understanding of expected standards; half day x 3 teachers per school  ***Reflection:*** Four-hour opportunity for teachers to review survey findings and plan next steps for ongoing improvement | Reform support funding: $198,000  Other funding: $0  FTE: 0TRS: $195,000  Travel and Accommodation: $2,000  Catering: $1,000 | * Improved understanding of the NCCD across school leaders, class teachers and Learning Support specialists, as measured through surveys in the reflection phase * Consistent, quality practice across our schools in terms of evidence collection and collation, and decision-making about level of addressed need, as measured by strong correlation between preliminary and final NCCD lists * On-going improvement in NCCD related systems and processes across all schools as measured through surveys in the reflection phase | * 60 teachers complete the NCCD training program * Teams from every school are involved in formal moderation sessions * Every school submits an NCCD plan in November 2022, following Reflection workshops |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Existing and aspiring school leaders**   National Policy Initiative: Reform Direction B – Supporting teaching, school leadership and school improvement.  Bilateral Agreement Action: Support school leadership and school improvement through initiatives aimed at enhancing strategic leadership for existing and aspiring school leaders and school boards. | Three courses offered through QELi to develop leadership capacity across our system, as follows:   * Professional and Difficult conversations * Middle Leaders course * Teach like a Champion course   Leading Mathematics Education   * Six project schools, 20 participants * TRS, travel, accommodation, catering * Resources * Additional time allocation to each school | Reform support funding: $133,972  Other funding: $0  FTE: 0  Registration Costs: $98,725 Catering: $2,000 TRS, resources, travel and accommodation: $33,247 | School leaders are more confident and competent in leading difficult but necessary conversations in a professional way, as measured by exit surveys   * An increased number of middle leaders (25) understand the dimensions of leadership and feel more equipped to embrace the rewards and challenges of leadership, as measured by course evaluations * More skilful classroom teachers express greater confidence in instructional practices, behaviour management, ways of engaging students, and communicating with parents, as measured in exit surveys * Teams of teachers from participating schools are more confident in mathematical content knowledge and mathematical pedagogical content knowledge (as measured through end of year reflections) | * At least 60 teachers participate in the Professional and Difficult conversations course * 25 participants complete the Middle Leaders (online) course and provide positive evaluations * Leading Mathematics Education workshops are held as planned. All participants provide feedback indicating what they have learned and how this can be applied in the classroom. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Student wellbeing**   National Policy Initiative: Reform Direction B – Supporting teaching, school leadership and school improvement.  Bilateral Agreement Action: Facilitate support to school communities in rural and remote areas to enhance student wellbeing. | Royal Far West counselling support for students in Blackall, Longreach, Barcaldine, Springsure, Clermont, Biloela, and Monto. | Reform support funding: $122,320  Other funding: $0  FTE: 0 | * Students have access to high quality counselling services. As a result, higher levels of student wellbeing enable greater engagement in learning at school | * Students access counselling services as required * The Head of Counselling Services reports high levels of satisfaction with quality and timeliness of counselling provided by Royal Far West |

# **Non-Government Reform Support Fund**

# **2022 Workplan**

# **Townsville Catholic Education**

### **Summary of Budget – Townsville Catholic Education**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project** | **Activities** | **Reform support funding** | **Funding from other sources** | **Total project funding** |
| **Student Wellbeing** | LOVE BiTES Respectful Relationships Program | $16,000 | $0 | $16,000 |
| **Early Years** | Support Early Years Teachers’ implementation of pre and post testing for literacy and numeracy | $81,512 | $43,488 | $125,000 |
| **HAT / LT Certification** | Support teachers’ participation in Highly Accomplished and Lead Teacher certification processes | $25,000 | $0 | $25,000 |
| **PIVOT** | Teachers in our secondary schools will engage in the PIVOT student voice surveys | $25,000 | $0 | $25,000 |
| **Leadership Development** | ‘Leading from Within’ Middle Leaders’ Program | $40,000 | $0 | $40,000 |
| **Leadership Development** | Aspirant Leaders’ Program (Western Region) | $35,000 | $0 | $35,000 |
| **Leadership Development** | 7 Habits of Highly Effective Leaders Program | $35,000 | $0 | $35,000 |
| **SMART IE Data** | School Motivation and Response to Indigenous Education (SMART IE) Data Project | $80,000 | $0 | $80,000 |
|  | **Total funding for 2022** | **$337,512** | **$43,488** | **$381,000** |

## **Non-Government Reform Support Fund**

### **Townsville Catholic Education Workplan 2022**

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| **1. LOVE BiTES Respectful Relationships Program**  National Policy Initiative:Reform Direction B – Support teaching, school leadership and school improvement  Bilateral Agreement Action:Reform Direction B - Facilitate support to school communities in rural and remote areas to enhance student wellbeing | LOVE BiTES aims to provide approximately 150 young people with a safe environment to examine, discuss and explore respectful relationships. All LOVE BiTES programming takes a strength-based approach and views young people as active participants who are able to make choices for themselves and their relationships when supported with information and opportunity for skill development.  This program provides facilitative support to school communities in rural and remote areas to enhance student wellbeing. | Reform support funding: $16,000  Other funding: $0  FTE: 0 | LOVE BiTES education is focused on three critical areas for learning:   * Knowledge: youth-led collaborative learning. * Attitudes: critical thinking and decision-making * Behaviours: problem-solving and communication skills | LOVE BiTES education will assist approximately 150 young people to:   * Increase their knowledge through youth-led collaborative learning around appropriate and safe relationships. * Challenge attitudes through critical thinking and decision-making. * Develop safe and proactive behaviours problem-solving and communication skills. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| **2. Early Years Literacy and Numeracy Data**  National Policy Initiative:  Reform Direction A - Supporting students, student learning and student achievement  Bilateral Agreement Action:  Reform Direction A - Review and extend early years screening tools in Queensland Catholic schools | The Early Years Literacy and Numeracy Data Project consists of an Oral Language and Numeracy screening tool for Prep and Year 1 students, and a Numeracy and Literacy test for Year 2 students. The data gathered is shared with the class teachers and with other key school personnel.  The early year teachers have the opportunity to plan for the students’ learning across the next two terms before a post testing occurs to indicate the progress the students have made. | Reform support funding: $81,512  Other funding: $43,488  FTE: 0.56 | * Teachers implement the pre- and post-tests in Years 1 and 2 at the designated times and make use of the data to plan and address the learning needs of the students. * They will use the data, along with other data to firstly plan for the next step in students’ learning and at the end of the year, assess the progress the students have made. | * 120 teachers from Prep to Year 2 will participate in pre-testing their students and in Term 3 undertake post testing to support them in planning for the range of learners in their class. * 120 teachers participate in the pre and post data sharing meetings. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| **3. Highly Accomplished Teacher and Lead Teacher Certification**  National Policy Initiative:  Reform Direction B – Support teaching, school leadership and school improvement  Bilateral Agreement Action:  Reform Direction B - Recognise the explicit value of teaching experience and proven ability in the classroom by rewarding highly accomplished and lead teachers | This project intends to provide strong strategic and systematic support for teachers embarking on the certification process ensuring they can effectively navigate the process and attain certification.  Work will also be undertaken to ensure school and system procedures and expectations align to support those teachers who wish to apply for certification.  Funding will support up to 10 teachers across the diocese to complete their portfolio for certification as a Highly Accomplished or Lead Teacher.  Three TRS days will be allocated to each applicant to allow time to gather evidence to address the 37 descriptors. Timing for teacher release will be negotiated with the applicant's Principal.  An online survey will be implemented to seek feedback from certification applicants and their principals regarding the satisfaction of support that is provided. | Reform support funding: $25,000  Other funding: $0  FTE: 0 | * Certification applicants gain an in-depth understanding of the requirements and expectations of the certification process. * Applicants develop a robust and authentic understanding of their own professional practice, strengths and development goals ensuring the alignment between the Teacher Appraisal/Performance processes and practices that align with APST. * Principals gain increased knowledge of certification requirements to enable their support of teachers’ participation in the certification process. * Ongoing mentoring will be provided to a certification applicant who withdraws and does not submit their application to enable that teacher to submit their application by the due date in the following year. | * 100% of certification applicants will each complete their portfolio and submit the portfolio to QCT for assessment. * Increased understanding of the certification process and at least one teacher from Townsville applies for certification |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| **4. PIVOT Student Voice Project**  National Policy Initiative:  Reform Direction B – Support teaching, school leadership and school improvement  Bilateral Agreement Action: Reform Direction B - Enhance school improvement processes and planning with Catholic schools | The 10 secondary schools across the diocese will implement this project by inviting teachers’ participation.  It is anticipated that 180 - 200 teachers will participate in 2022.  Teachers will participate by having students complete an online feedback process regarding the impact of the teacher’s practice in line with the AITSL standards.  This survey is conducted twice in the year. | Reform support funding: $25,000  Other funding: $0  FTE: 0 | * Teachers can identify areas of their teaching practice where they can develop and improve based on the student feedback. * Principals can use the overall school data to target professional development with teachers and to support teachers to engage in a rigorous PLP process.      * Principals and other school leaders can identify areas of growth and development in students’ learning, engagement and differentiation. * System Learning and Teaching Advisers can use the overall diocesan data to target professional development of teachers and to inform networking opportunities. | * Approximately 150 teachers engage with the PIVOT survey * Teachers will have just-in-time data to assist them to identify areas of success, growth and development about their teaching. * Teachers will be more receptive to undertaking professional coaching with school leaders to improve their teaching pedagogy. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| **5. School Motivation and Response to Indigenous Education (SMART IE) Data Project**  National Policy Initiative:Reform Direction B -Support teaching, school leadership and school improvement  Bilateral Agreement Action:Reform Direction C - Develop strategies to enhance data literacy among Catholic school leaders and teachers, support development of data tools and frameworks to inform planning and development of education policy and practices in Catholic schools, and support roll out of NAPLAN Online to Catholic schools | The project intends to form and improve the competency and capacity of school leaders to implement data informed practices in Indigenous Education in schools with a particular focus on First Nations student NAPLAN data.  A Project Officer will be employed for 10 months to:   * manage the collation and accessibility of TCE IE data, particularly NAPLAN data * engage with data analysis expertise to prepare relevant data sets * prepare and facilitate professional learning for school leaders on driving data informed practices for improved First Nations student outcomes * support Indigenous Education Advisers in their roles to coach school leaders to enable enhanced responses to IE data sets, planning for school improvement, aligning strategic actions and improving the academic outcomes of First Nations students in TCE. | Reform support funding: $80,000  Other funding: $0  FTE: 0.8 | * Alignment of IE data sets to TCE and IE strategic actions and work plans. * Stakeholders have improved access to relevant data sets. * Data sets are fit for purpose: clean, valid, reliable, objective, comparable. * Project facilitates improved system, school and student data informed practices and outcomes. * Improved capacity of stakeholders to respond effectively to NAPLAN data particularly as this relates to First Nations students. | * School leaders lead SMART IE Data practices in their own schools and build school improvement around informed needs in Indigenous Education. * TCE First Nations students NAPLAN results indicate improvement over time. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| **6. Leadership Development**  National Policy Initiative: Reform Direction B – Support teaching, school leadership and school improvement  Bilateral Agreement Action: Reform Direction B - Support school leadership and school improvement through initiatives aimed at enhancing strategic leadership for existing and aspiring school leaders and for school boards | These initiatives will support school leadership and school improvement by implementing professional learning programs which enhance the skills, knowledge and capabilities of current and aspiring leaders.  Programs intended to be delivered include:   * Leading from Within Middle Leaders’ Program (The Brown Collective) * Aspirant Leaders’ Program (Western Region) (TCEO Program) * 7 Habits of Highly Effective Leaders (QELI) | Reform support funding: $110,000  Other funding: $0  FTE: 0 | * Improvement of school leaders’ skills in the areas of: * governance and decision making; * strategic and operational capabilities; * influence and interpersonal skills; * school improvement; and * leading others and supporting effective performance. * Improved skills, knowledge, and readiness of those aspiring to school leadership in the future. * Opportunities for experienced leaders to self-reflect and identify areas of development. * Increased knowledge and awareness of the role of leaders in our Catholic schools. | * Targeted invitees participate in the Aspirant Leaders’ Program (Western Region), Leading from Within Middle Leaders’ Program, and 7 Habits of Highly Effective People program. * Feedback collected confirms participants’ reflections regarding increased leadership competence * Increased number of aspiring leaders indicate interest in acting or permanent senior leadership positions. * Increased number of applicants for middle and senior leadership positions. |

# **Non-Government Reform Support Fund**

# **2022 Workplan**

# **Catholic Education - Cairns**

### **Summary of Budget – Catholic Education – Cairns**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project** | **Activities** | **2022**  **Reform support funding** | **Funding from other sources** | **2022 Total project funding** |
| **NCCD** | Support for local projects and engagement in QCEC Central projects to support the Nationally Consistent Collection of Data on Students with Disability. | $106,000 | $0 | $106,000 |
| **Clarity – An approach to system-wide school improvement** | A program to support schools to focus on the 14 parameters of System and School Improvement as outlined in the text by Sharratt, *Clarity – What Matters Most in Learning, Teaching and Leading.* | $200,530 | $80,000 | $280,530 |
|  | **Total funding for 2022** | **$306,530** | **$80,000** | **$386,530** |

\* The Australian Government understands that these figures provided are indicative and may change throughout the year. The Annual Report will report on any changes.

## **Non-Government Reform Support Fund**

### **Catholic Education Cairns Workplan 2022**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| **1.** **Nationally Consistent Collection of Data on Students with Disability (NCCD) Local**  **National Policy Initiative:** Reform Direction C – Enhancing the national evidence base  **Reform Support Fund priority 7(a):** Quality assurance, moderation, and support for the continued improvement of the Nationally Consistent Collection of Data on School Students with Disability | Cairns Catholic Education (CES) led: Local support led by CES to strengthen quality assurance, moderation, and support for the continued improvement of the Nationally Consistent Collection of Data for students with disability.  Key focus areas:   * In-school moderation activities * Individual schools’ completion of NCCD Reflection Tool and forward planning for next cycle   QCEC led: Engagement in Central Project led by QCEC personnel to strengthen quality assurance, moderation, and support for the continued improvement of the Nationally Consistent Collection of Data for students with disability.  Key focus area:   * Information sessions for new staff * Cross-school moderation sessions * Cross-Sector moderation sessions * Reflection sessions | Reform support funding: $106, 000  Other funding: $0  Leading Practice Session  NCCD Training, Moderation, Quality Assurance & Reflection:   * TRS * Travel, Accommodation and Meals as required * Venue & Catering as required * Resources | * Decisions regarding levels of adjustment and disability categories are identified as accurate through in-school moderation process * Goals are identified for improvement in the next cycle of NCCD * Improved confidence in decision-making by School Teams * Alignment of decisions regarding levels of adjustment and disability category between schools, CSAs, and Sectors | * Quality assurance process confirms the accuracy of schools’ decisions * CES NCCD data indicates alignment with NCCD Guidelines, 4 areas of Evidence and the criteria under these 4 areas of Evidence * Limited changes during quality assurance process after submission of preliminary data |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| **2. Clarity-An approach to systemwide school improvement**  **Reform Support Fund Priority:**   1. Supporting students, student learning and student achievement. 2. Supporting teaching, school leadership and school improvement   **Bilateral Reform Direction B:**  Reform Direction B – Support teaching, school leadership and school improvement - *Enhance school improvement processes and planning with Catholic schools* | Building on work commenced in 2021, CES will continue to work with Dr Lyn Sharratt in 2022. This work particularly focuses on the 14 parameters of System and School Improvement as outlined in the text by Sharratt, *Clarity - What Matters Most in Learning, Teaching, and Leading*.  School Leadership teams and new Catholic Education Services staff will undertake professional learning across the year and will provide professional learning to implement the specific practices with the staff of each school. The work is undertaken through the lens of writing or reading as per the school's Annual Improvement Plan and will focus on three common parameters and one of the school's choosing with the overarching goal to embed all 14 parameters as their ongoing work. The three common parameters are:  1. Shared beliefs and understandings  6. Case management approach,  14. Shared responsibility and accountability.  A project consultant is employed to support schools on the ground as they work through this project.  School leadership teams will engage via face-to-face Professional Development activities, ZOOM feedback sessions with Dr Sharratt and school-based projects throughout the year. CES staff will facilitate activities and support schools to embed the identified parameters. | Reform support funding:  $200,530  Other sources: $80,000 to support Consultant salary | * Schools report increased understanding of the 14 parameters as outlined by Dr Lyn Sharratt * Networks and partnerships with other schools have been built to impact student outcomes and smooth transitions * Schools report increased confidence amongst staff to use Data Walls and evidence to inform practice and goal setting. * The project consultant is in regular contact with the participating schools and monitors progress. | * Data Walls are constructed based on school data aligned with the School’s Annual Improvement Plan goal * Instructional Case Management meetings are conducted in all (30) schools to target specific strategies to progress students identified by the Data Wall. * Professional Development to build staff capacity to embed the parameters is undertaken in all (30) schools. * Students show improved learning growth in school identified improvement area. |

# **Non-Government Reform Support Fund**

# **2022 Workplan**

# **Diocese of Toowoomba Catholic Schools**

### **Summary of Budget – Diocese of Toowoomba**

| **Project** | **Activities** | **Reform support funding** | **Funding from other sources** | **Total project funding** |
| --- | --- | --- | --- | --- |
| **NAPLAN and HALT** | Toowoomba Catholic Schools Office and school staff will continue to engage with QCEC-led activities to support the transition to NAPLAN Online as well as Highly Accomplished and Lead Teacher applications. | $0 | $0 | $0 |
| **NCCD** | Toowoomba Catholic Schools Office and school staff will participate in the QCEC NCCD project activities, including training, moderation and reflection regarding the NCCD to upskill teachers and leadership on processes for continued improvement of NCCD.  Office staff will continue to work with school staff to increase capacity and knowledge and work towards consistency of judgement. | $20,000 | $20,000 | $40,000 |
| **Digital and data literacy** | In-services and support to schools in developing data literacy and data planning capabilities in schools. | $47,139 | $1,000 | $48,139 |
| **Leadership learning program – Middle leaders** | Services across primary and secondary year levels with associated expenses including TRS, travel, catering, accommodation costs, resources across the year.  Engage and develop familiarity with key systems, strategic documents and expectations including TCS leadership.  Facilitate ongoing networking and collaboration between middle leaders and established system and school leaders. | $29,000 | $0 | $29,000 |
| **Leadership learning program - Deputisers** | In-services across primary and secondary year levels with associated expenses including TRS, travel, catering, accommodation costs, resources across the year.  Ensure sufficient knowledge of and familiarity with key responsibilities associated with the deputiser’s role.  Engage and develop familiarity with the Toowoomba Catholic Schools Leadership Framework and capabilities.  Facilitate ongoing networking and collaboration between deputisers and established school and system leaders. | $25,000 | $0 | $25,000 |
| **School review and improvement processes** | Implementation of the program within the school environment with costs including TRS for staff involved from within the school and other schools, consultancy fees, travel and accommodation costs.  Support the work of school leaders, staff, students and community in evaluating the effectiveness of programs and directions against agreed goals and priorities.  Develop capabilities and practices associated with effective strategic planning and decision making.  Ensure local and system accountability to school communities and the government for the prudent oversight of resources and staffing to attain the desired student outcomes. | $72,000 | $0 | $72,000 |
| **Peoplebench Project** | Engagement costs for Peoplebench organisation for 2022.  Utilise predictive analytics to assist leaders to make data-driven predictions based on behaviour and trends.  Enhance the capacity of principals and other system leaders to effectively utilise this data to inform strategic planning and decision-making. | $48,825 | $0 | $48,825 |
|  | **Total funding for 2022** | **$241,964** | **$21,000** | **$262,964** |

\* The Australian Government understands that these figures provided are indicative and will change throughout the year. The Annual Report is expected to report on these changes.

## **Non-Government Reform Support Fund**

### **Toowoomba Catholic Education Workplan 2022**

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Project title: Quality assurance, moderation and support for continued improvement of the NCCD**   Bilateral Reform Direction C – Enhancing the national evidence base. | Toowoomba Catholic Schools staff will engage in professional development NCCD update sessions centrally coordinated by QCEC.  School staff will be supported to attend NCCD update sessions through provision of teacher relief funds, travel and accommodation costs.  Support will be provided by Toowoomba Catholic Schools Office (TCSO) education officers and managers for the NCCD and personalised student planning support to all schools.  All QCEC facilitated sessions plus specific targeted sessions that are in addition to the one-on-one support provided to schools are as follows:   * Early careers NCCD professional development sessions – online and face to face options (4) * Planning for personalised learning training sessions that incorporate elements that feed into NCCD (2) * Learning Support Teacher network professional development days that incorporate NCCD education (2) | Reform support funding: $20,000  Other funding: $20,000  FTE: 0.75 | * Confidence in the accuracy of the school level data submitted for census. * Delivery of professional learning about the NCCD. * Teachers are better equipped to plan, record and monitor educational adjustments for students with disability within the four phases of the NCCD. * NCCD within school moderation processes are embedded in the school cycle. | * Feedback from participants surveyed indicate improved understanding of the NCCD * Approximately 25 school staff will attend NCCD update sessions. * Review of schools’ NCCD will find appropriate evidence for NCCD decisions. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Project title: Enhancing school improvement processes through data and digital literacy development**   Bilateral Reform Direction C – Enhancing the national evidence base. | This project will provide professional development opportunities and support to schools in developing data literacy, as well as support schools in developing their digital literacy and data planning capability.  There will be two formal Digital Literacy professional development sessions held in 2022. | Reform support funding: $47,139  Other funding: $1,000  FTE: 0.25 | * Enhanced school staff capacity and confidence in the use of data and digital tools to support and inform decision making to support student performance through differentiated responses. | * School staff will have improved confidence in choosing appropriate interventions and/or adjustments which accommodate individual student learning attributes. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Project title: Leadership learning program – Middle leaders**   Bilateral Reform Direction B – Support teaching, school leadership and school improvement. | The purpose of this program is to provide opportunities for middle leaders to:   1. Engage with and develop familiarity with key system and strategic documents and expectations including TCS Leadership Framework and capabilities 2. Examine and evaluate personal leadership styles, strengths and deficits 3. Develop professional learning plans to target specific areas of growth 4. Facilitate ongoing networking and collaboration between middle leaders and established system and school leaders | Reform support funding: $29,000  Other funding: $0  FTE: 0.1 | * Increased familiarity of Middle Leaders with TCS organisational structure, culture, and priorities. * Understanding the connection between leadership capabilities and school and system leadership. * Opportunity to reflect and evaluate personal strengths and practices within a supportive and professional network of established system and school leaders | * Feedback surveys from participants endorse the learning intentions for each workshop. * Increased level of interest applications for middle leadership positions. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Project title: Leadership learning program – Deputisers**   Bilateral Reform Direction B – Support teaching, school leadership and school improvement. | The purpose of this program is to provide opportunities for 30 deputisers to:   1. Ensure sufficient knowledge of and familiarity with key responsibilities associated with the deputiser role 2. Engage and develop familiarity with the TCS Leadership Framework and capabilities 3. Facilitate ongoing networking and collaboration between deputisers and established system and school leaders   Program delivery is expected to be face-to-face. | Reform support funding: $25,000  Other funding: $0  FTE: 0.1 | * Deputisers are confident in managing the required responsibilities associated with the role. * Continuity of student learning and school routines when the principal is absent. * Deputisers experience and develop further capacity in a variety of responsibilities associated with the principal’s role. | * Feedback surveys from participants endorse the learning intentions for each workshop. * Participants indicate improved knowledge of their capability as a leader and opportunities for future growth |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Project title: School review and improvement processes**   Bilateral Reform Direction B – Support teaching, school leadership and school improvement. | The purpose of this program is to:   1. Support the work of school leaders, staff, students and community in evaluating the effectiveness of programs and directions against agreed goals and priorities 2. Develop capabilities and effective practices associated with effective strategic planning and decision making 3. Ensure local and system accountability to school communities and government for the prudent oversight of resources and staffing to attain the desired student outcomes | Reform support funding: $72,000  Other funding: $0  FTE: 0.2 | * School communities have a formal and structured avenue to provide feedback on key elements of the operation of the school. * School leaders have access to independent, valid feedback about school performance. * The system uses the outcomes of this process to ensure accountability to school communities and government for the prudent oversight of resources and staffing to attain the desired student outcomes. | * Feedback from school communities confirms high satisfaction levels with the process and outcomes. * Principals indicate that they will use the improvement strategies listed in the report as a basis for future planning. * Annual parent surveys reflect high satisfaction levels with the goals, priorities, and direction of schools. |

| **Project title** | **Project description and activities** | **Indicative budget** | **Expected outcomes/**  **Overall achievements** | **Indicators of success** |
| --- | --- | --- | --- | --- |
| 1. **Project title: Peoplebench project**   Bilateral Reform Direction C – Enhancing the national evidence base | The aim of this project is to:   1. Use predictive analytics to assist leaders to make data-driven predictions based on behaviour and trends focussed on workforce strategies. 2. Enhance the capacity of system leaders to effectively utilise this data to inform strategic planning and decision making. | Reform support funding: $48,825  Other funding: $0  FTE: N/A | * Benchmark data across large numbers of schools enables prudent decisions about future planning and action. * Toowoomba Catholic Schools can compare and contrast current practice in key areas against schools and systems with similar contexts. * Available data is current and timely and reflects changing workforce trends and patterns. | * System leaders report a greater capacity to use data to inform strategic planning and decision making. |

### **A full list of schools has been provided below:**

| **AGEID** | **School Name** | **Catholic School Authority** |
| --- | --- | --- |
| 5610 | All Saints Primary School, ALBANY CREEK | Archdiocese of Brisbane CEO |
| 409 | All Saints' School, BOONAH | Archdiocese of Brisbane CEO |
| 411 | Aquinas College, ASHMORE | Archdiocese of Brisbane CEO |
| 18057 | Assisi Catholic College, UPPER COOMERA | Archdiocese of Brisbane CEO |
| 13460 | Carmel College, THORNLANDS | Archdiocese of Brisbane CEO |
| 13480 | Chisholm Catholic College, CORNUBIA | Archdiocese of Brisbane CEO |
| 2528 | Christ the King Catholic Primary School, DECEPTION BAY | Archdiocese of Brisbane CEO |
| 428 | Christ the King School, GRACEVILLE | Archdiocese of Brisbane CEO |
| 5523 | Clairvaux MacKillop College, UPPER MOUNT GRAVATT | Archdiocese of Brisbane CEO |
| 17163 | Emmaus College, JIMBOOMBA | Archdiocese of Brisbane CEO |
| 84930 | Good Samaritan Catholic College, BLI BLI | Archdiocese of Brisbane CEO |
| 30006 | Good Shepherd Catholic Primary School, SPRINGFIELD LAKES | Archdiocese of Brisbane CEO |
| 448 | Guardian Angels' Catholic Primary School, ASHMORE | Archdiocese of Brisbane CEO |
| 449 | Guardian Angels' Primary School, WYNNUM | Archdiocese of Brisbane CEO |
| 451 | Holy Cross School, WOOLOOWIN | Archdiocese of Brisbane CEO |
| 453 | Holy Family Primary School, INDOOROOPILLY | Archdiocese of Brisbane CEO |
| TBA | Holy Spirit College, FITZGIBBON (Opening in 2022) | Archdiocese of Brisbane CEO |
| 2513 | Holy Spirit School, BRAY PARK | Archdiocese of Brisbane CEO |
| 458 | Holy Spirit School, NEW FARM | Archdiocese of Brisbane CEO |
| 460 | Immaculate Heart School, LEICHHARDT | Archdiocese of Brisbane CEO |
| 16689 | Jubilee Primary School, PACIFIC PINES | Archdiocese of Brisbane CEO |
| 475 | Mary Immaculate Primary School, ANNERLEY | Archdiocese of Brisbane CEO |
| 17230 | Mary MacKillop College, NUNDAH | Archdiocese of Brisbane CEO |
| 476 | Marymount College, BURLEIGH WATERS | Archdiocese of Brisbane CEO |
| 2249 | Marymount Primary School, BURLEIGH WATERS | Archdiocese of Brisbane CEO |
| 477 | Mater Dei Catholic Primary School, ASHGROVE WEST | Archdiocese of Brisbane CEO |
| 30269 | McAuley College, BEAUDESERT | Archdiocese of Brisbane CEO |
| 28619 | Mother Teresa Primary School, ORMEAU | Archdiocese of Brisbane CEO |
| 5509 | Mt Maria College - Petrie, PETRIE | Archdiocese of Brisbane CEO |
| 2522 | Mt Maria College, MITCHELTON | Archdiocese of Brisbane CEO |
| 491 | Our Lady Help of Christians School, HENDRA | Archdiocese of Brisbane CEO |
| 494 | Our Lady of Dolours School, MITCHELTON | Archdiocese of Brisbane CEO |
| 495 | Our Lady of Fatima Primary School, ACACIA RIDGE | Archdiocese of Brisbane CEO |
| 496 | Our Lady of Good Counsel School, GATTON | Archdiocese of Brisbane CEO |
| 497 | Our Lady of Lourdes Primary School, SUNNYBANK | Archdiocese of Brisbane CEO |
| 501 | Our Lady of Mount Carmel School, COORPAROO | Archdiocese of Brisbane CEO |
| 502 | Our Lady of the Angels' School, WAVELL HEIGHTS | Archdiocese of Brisbane CEO |
| 503 | Our Lady of the Assumption School, ENOGGERA | Archdiocese of Brisbane CEO |
| 2533 | Our Lady of the Rosary School, CALOUNDRA | Archdiocese of Brisbane CEO |
| 505 | Our Lady of the Rosary School, KENMORE | Archdiocese of Brisbane CEO |
| 516 | Our Lady of the Sacred Heart Catholic Primary School, DARRA | Archdiocese of Brisbane CEO |
| 510 | Our Lady of the Way School, PETRIE | Archdiocese of Brisbane CEO |
| 512 | Our Lady's College, ANNERLEY | Archdiocese of Brisbane CEO |
| 2509 | Queen of Apostles Primary School, STAFFORD | Archdiocese of Brisbane CEO |
| 526 | Sacred Heart Primary School, SANDGATE | Archdiocese of Brisbane CEO |
| 520 | Sacred Heart School, BOOVAL | Archdiocese of Brisbane CEO |
| 13621 | Saint Mary's Catholic College, KINGAROY | Archdiocese of Brisbane CEO |
| 86328 | San Damiano College (Yarrabilba), YARRABILBA | Archdiocese of Brisbane CEO |
| 720 | San Sisto College, CARINA | Archdiocese of Brisbane CEO |
| 722 | Seton College, MOUNT GRAVATT EAST | Archdiocese of Brisbane CEO |
| 14676 | Siena Catholic College, SIPPY DOWNS | Archdiocese of Brisbane CEO |
| 17164 | Siena Catholic Primary School, SIPPY DOWNS | Archdiocese of Brisbane CEO |
| 87134 | Sophia College (Plainland) , PLAINLAND | Archdiocese of Brisbane CEO |
| 14311 | Southern Cross Catholic College, SCARBOROUGH | Archdiocese of Brisbane CEO |
| 529 | St Agatha's Primary School, CLAYFIELD | Archdiocese of Brisbane CEO |
| 530 | St Agnes School, MOUNT GRAVATT | Archdiocese of Brisbane CEO |
| 532 | St Ambrose's Primary School, NEWMARKET | Archdiocese of Brisbane CEO |
| 4274 | St Andrew's Catholic School, FERNY GROVE | Archdiocese of Brisbane CEO |
| 86442 | St Ann's School, REDBANK PLAINS | Archdiocese of Brisbane CEO |
| 2539 | St Anthony's School, ALEXANDRA HILLS | Archdiocese of Brisbane CEO |
| 536 | St Anthony's School, KEDRON | Archdiocese of Brisbane CEO |
| 17525 | St Augustine's College, AUGUSTINE HEIGHTS | Archdiocese of Brisbane CEO |
| 540 | St Augustine's Parish Primary School, CURRUMBIN WATERS | Archdiocese of Brisbane CEO |
| 30010 | St Benedict's College, MANGO HILL | Archdiocese of Brisbane CEO |
| 26010 | St Benedict's Primary School, MANGO HILL | Archdiocese of Brisbane CEO |
| 544 | St Bernard's School, UPPER MOUNT GRAVATT | Archdiocese of Brisbane CEO |
| 2552 | St Bernardine's School, REGENTS PARK | Archdiocese of Brisbane CEO |
| 546 | St Brendan's Primary School, MOOROOKA | Archdiocese of Brisbane CEO |
| 13763 | St Brigid's Catholic Primary School, NERANG | Archdiocese of Brisbane CEO |
| 548 | St Brigid's Primary School, ROSEWOOD | Archdiocese of Brisbane CEO |
| 2147 | St Catherine's Catholic Primary School, WISHART | Archdiocese of Brisbane CEO |
| 30270 | St Clare's Primary School, YARRABILBA | Archdiocese of Brisbane CEO |
| 558 | St Columba's Primary School, WILSTON | Archdiocese of Brisbane CEO |
| 554 | St Columban's College, CABOOLTURE | Archdiocese of Brisbane CEO |
| 560 | St Dympna's Parish School, ASPLEY | Archdiocese of Brisbane CEO |
| 2521 | St Edward the Confessor School, DAISY HILL | Archdiocese of Brisbane CEO |
| 563 | St Elizabeth's School, TARRAGINDI | Archdiocese of Brisbane CEO |
| 13180 | St Eugene College, BURPENGARY | Archdiocese of Brisbane CEO |
| 564 | St Finbarr's School, ASHGROVE | Archdiocese of Brisbane CEO |
| 566 | St Flannan's School, ZILLMERE | Archdiocese of Brisbane CEO |
| 2511 | St Francis Xavier School, RUNAWAY BAY | Archdiocese of Brisbane CEO |
| 575 | St Francis Xavier's School, GOODNA | Archdiocese of Brisbane CEO |
| 5609 | St Francis' College, CRESTMEAD | Archdiocese of Brisbane CEO |
| 579 | St Ignatius School, TOOWONG | Archdiocese of Brisbane CEO |
| 580 | St Ita's Regional Primary School, DUTTON PARK | Archdiocese of Brisbane CEO |
| 582 | St James Primary School, COORPAROO | Archdiocese of Brisbane CEO |
| 583 | St Joachim's School, HOLLAND PARK | Archdiocese of Brisbane CEO |
| 521 | St John Fisher College, BRACKEN RIDGE | Archdiocese of Brisbane CEO |
| 589 | St John Vianney's Primary School, MANLY | Archdiocese of Brisbane CEO |
| 2202 | St John's College, NAMBOUR | Archdiocese of Brisbane CEO |
| 2520 | St Joseph's Catholic Primary School, BRACKEN RIDGE | Archdiocese of Brisbane CEO |
| 84936 | St Joseph's College, SOUTH COOMERA | Archdiocese of Brisbane CEO |
| 609 | St Joseph's Primary School, CORINDA | Archdiocese of Brisbane CEO |
| 621 | St Joseph's Primary School, KANGAROO POINT | Archdiocese of Brisbane CEO |
| 601 | St Joseph's Primary School, NAMBOUR | Archdiocese of Brisbane CEO |
| 614 | St Joseph's School, BARDON | Archdiocese of Brisbane CEO |
| 615 | St Joseph's School, CHILDERS | Archdiocese of Brisbane CEO |
| 619 | St Joseph's School, GAYNDAH | Archdiocese of Brisbane CEO |
| 625 | St Joseph's School, MURGON | Archdiocese of Brisbane CEO |
| 602 | St Joseph's School, NORTH IPSWICH | Archdiocese of Brisbane CEO |
| 610 | St Joseph's School, NUNDAH | Archdiocese of Brisbane CEO |
| 631 | St Joseph's Tobruk Memorial School, BEENLEIGH | Archdiocese of Brisbane CEO |
| 2527 | St Kevin's School, BENOWA | Archdiocese of Brisbane CEO |
| 632 | St Kevin's School, GEEBUNG | Archdiocese of Brisbane CEO |
| 634 | St Kieran's School, BRIGHTON | Archdiocese of Brisbane CEO |
| 5917 | St Luke's Catholic Parish School, CAPALABA | Archdiocese of Brisbane CEO |
| 641 | St Mark's School, INALA | Archdiocese of Brisbane CEO |
| 642 | St Martin's School, CARINA | Archdiocese of Brisbane CEO |
| 14583 | St Mary MacKillop Primary School, BIRKDALE | Archdiocese of Brisbane CEO |
| 455 | St Mary of the Cross School, WINDSOR | Archdiocese of Brisbane CEO |
| 654 | St Mary's College, IPSWICH | Archdiocese of Brisbane CEO |
| 427 | St Mary's College, MARYBOROUGH | Archdiocese of Brisbane CEO |
| 658 | St Mary's Primary School, IPSWICH | Archdiocese of Brisbane CEO |
| 659 | St Mary's Primary School, MARYBOROUGH | Archdiocese of Brisbane CEO |
| 648 | St Mary's School, BEAUDESERT | Archdiocese of Brisbane CEO |
| 651 | St Mary's School, LAIDLEY | Archdiocese of Brisbane CEO |
| 4053 | St Matthew's School, CORNUBIA | Archdiocese of Brisbane CEO |
| 4275 | St Michael's College, MERRIMAC | Archdiocese of Brisbane CEO |
| 413 | St Oliver Plunkett School, CANNON HILL | Archdiocese of Brisbane CEO |
| 679 | St Patrick's College, GYMPIE | Archdiocese of Brisbane CEO |
| 681 | St Patrick's Primary School, GYMPIE | Archdiocese of Brisbane CEO |
| 675 | St Patrick's Primary School, NANANGO | Archdiocese of Brisbane CEO |
| 687 | St Paul's School, WOODRIDGE | Archdiocese of Brisbane CEO |
| 694 | St Peter Chanel Primary School, THE GAP | Archdiocese of Brisbane CEO |
| 2204 | St Peter Claver College, RIVERVIEW | Archdiocese of Brisbane CEO |
| 691 | St Peter's Catholic Primary School, CABOOLTURE | Archdiocese of Brisbane CEO |
| 2504 | St Peter's Primary School, ROCHEDALE | Archdiocese of Brisbane CEO |
| 696 | St Pius X School, SALISBURY | Archdiocese of Brisbane CEO |
| 695 | St Pius' Primary School, BANYO | Archdiocese of Brisbane CEO |
| 13771 | St Rita's Primary School, VICTORIA POINT | Archdiocese of Brisbane CEO |
| 702 | St Sebastian's Primary School, YERONGA | Archdiocese of Brisbane CEO |
| 17747 | St Stephen's School, ALGESTER | Archdiocese of Brisbane CEO |
| 17748 | St Teresa's Catholic College, NOOSAVILLE | Archdiocese of Brisbane CEO |
| 2505 | St Thomas More College, SUNNYBANK | Archdiocese of Brisbane CEO |
| 13181 | St Thomas More Primary School, SUNSHINE BEACH | Archdiocese of Brisbane CEO |
| 710 | St Thomas' School, CAMP HILL | Archdiocese of Brisbane CEO |
| 717 | St Vincent's Primary School, CLEAR ISLAND WATERS | Archdiocese of Brisbane CEO |
| 718 | St William's Primary School, KEPERRA | Archdiocese of Brisbane CEO |
| 4052 | Star of the Sea Catholic School, TORQUAY | Archdiocese of Brisbane CEO |
| 27819 | Star of the Sea Primary School, CLEVELAND | Archdiocese of Brisbane CEO |
| TBA | Star of the Sea School, MERRIMAC (Opening in 2022) | Archdiocese of Brisbane CEO |
| 2534 | Stella Maris School, MAROOCHYDORE | Archdiocese of Brisbane CEO |
| 689 | Sts Peter and Paul's School, BULIMBA | Archdiocese of Brisbane CEO |
| 2544 | Trinity College, BEENLEIGH | Archdiocese of Brisbane CEO |
| 18220 | Unity College, CALOUNDRA WEST | Archdiocese of Brisbane CEO |
| 17524 | Xavier Catholic College, HERVEY BAY | Archdiocese of Brisbane CEO |
| 17580 | Good Counsel College, INNISFAIL | Diocese of Cairns CES |
| 17581 | Good Counsel Primary School, INNISFAIL | Diocese of Cairns CES |
| 5513 | Holy Cross School, TRINITY PARK | Diocese of Cairns CES |
| 30210 | Holy Spirit College, COOKTOWN | Diocese of Cairns CES |
| 30177 | MacKillop Catholic College, MOUNT PETER | Diocese of Cairns CES |
| 481 | Mother of Good Counsel School, CAIRNS NORTH | Diocese of Cairns CES |
| 17244 | Mount St Bernard College, HERBERTON | Diocese of Cairns CES |
| TBA | Newman Catholic College, SMITHFIELD (Opening in 2022) | Diocese of Cairns CES |
| 490 | Our Lady Help of Christians School, EARLVILLE | Diocese of Cairns CES |
| 508 | Our Lady of the Sacred Heart School, THURSDAY ISLAND | Diocese of Cairns CES |
| 16688 | St Andrew's Catholic College Redlynch Valley, REDLYNCH | Diocese of Cairns CES |
| 535 | St Anthony's School, DIMBULAH | Diocese of Cairns CES |
| 17218 | St Augustine's College, CAIRNS | Diocese of Cairns CES |
| 541 | St Augustine's School, MOSSMAN | Diocese of Cairns CES |
| 552 | St Clare's School, TULLY | Diocese of Cairns CES |
| 574 | St Francis Xavier's School, MANUNDA | Diocese of Cairns CES |
| 5612 | St Gerard Majella Primary School, WOREE | Diocese of Cairns CES |
| 586 | St John's School, SILKWOOD | Diocese of Cairns CES |
| 30180 | St Joseph's Parish School, WEIPA | Diocese of Cairns CES |
| 613 | St Joseph's School, ATHERTON | Diocese of Cairns CES |
| 603 | St Joseph's School, PARRAMATTA PARK | Diocese of Cairns CES |
| 5528 | St Mary's Catholic College, WOREE | Diocese of Cairns CES |
| 665 | St Michael's School, GORDONVALE | Diocese of Cairns CES |
| 17231 | St Monica's College, CAIRNS | Diocese of Cairns CES |
| 698 | St Rita's School, BABINDA | Diocese of Cairns CES |
| 699 | St Rita's School, SOUTH JOHNSTONE | Diocese of Cairns CES |
| 18059 | St Stephen's Catholic College, MAREEBA | Diocese of Cairns CES |
| 706 | St Teresa's School, RAVENSHOE | Diocese of Cairns CES |
| 708 | St Therese's School, BENTLEY PARK | Diocese of Cairns CES |
| 712 | St Thomas' School, MAREEBA | Diocese of Cairns CES |
| TBA | Catherine McAuley College, MACKAY (Opening in 2022) | Diocese of Rockhampton CEO |
| 16952 | Chanel College, GLADSTONE | Diocese of Rockhampton CEO |
| 15877 | Emmanuel Catholic Primary School, MOUNT PLEASANT | Diocese of Rockhampton CEO |
| 14048 | Emmaus College, PARK AVENUE | Diocese of Rockhampton CEO |
| 15878 | Holy Spirit College, MOUNT PLEASANT | Diocese of Rockhampton CEO |
| 14316 | MacKillop Catholic Primary School, ANDERGROVE | Diocese of Rockhampton CEO |
| 14750 | Marist College, EMERALD | Diocese of Rockhampton CEO |
| 17246 | Mercy College, MACKAY | Diocese of Rockhampton CEO |
| 507 | Our Lady of the Sacred Heart Catholic Primary School, SPRINGSURE | Diocese of Rockhampton CEO |
| 5565 | Our Lady's Catholic Primary School, LONGREACH | Diocese of Rockhampton CEO |
| 524 | Sacred Heart Catholic Primary School, YEPPOON | Diocese of Rockhampton CEO |
| 17228 | Shalom College, BUNDABERG | Diocese of Rockhampton CEO |
| 533 | St Anne's Catholic Primary School, SARINA | Diocese of Rockhampton CEO |
| 537 | St Anthony's Catholic Primary School, NORTH ROCKHAMPTON | Diocese of Rockhampton CEO |
| 26009 | St Benedict's Catholic Primary School, YEPPOON | Diocese of Rockhampton CEO |
| 30236 | St Brendan's Catholic Primary School, RURAL VIEW, MACKAY | Diocese of Rockhampton CEO |
| 30142 | St Brigid's Catholic Primary School, EMERALD | Diocese of Rockhampton CEO |
| 18221 | St Francis Catholic Primary School, TANNUM SANDS | Diocese of Rockhampton CEO |
| 572 | St Francis Xavier Catholic Primary School, MACKAY WEST | Diocese of Rockhampton CEO |
| 2514 | St John the Baptist Catholic Primary School, GLADSTONE | Diocese of Rockhampton CEO |
| 587 | St John's Catholic Primary School, WALKERSTON | Diocese of Rockhampton CEO |
| 595 | St Joseph's Catholic Primary School, BARCALDINE | Diocese of Rockhampton CEO |
| 596 | St Joseph's Catholic Primary School, BILOELA | Diocese of Rockhampton CEO |
| 597 | St Joseph's Catholic Primary School, BLACKALL | Diocese of Rockhampton CEO |
| 608 | St Joseph's Catholic Primary School, BUNDABERG | Diocese of Rockhampton CEO |
| 616 | St Joseph's Catholic Primary School, CLERMONT | Diocese of Rockhampton CEO |
| 626 | St Joseph's Catholic Primary School, NORTH MACKAY | Diocese of Rockhampton CEO |
| 604 | St Joseph's Catholic Primary School, PARK AVENUE | Diocese of Rockhampton CEO |
| 627 | St Joseph's Catholic Primary School, WANDAL | Diocese of Rockhampton CEO |
| 5822 | St Mary's Catholic Primary School, BUNDABERG | Diocese of Rockhampton CEO |
| 664 | St Mary's Catholic Primary School, MACKAY SOUTH | Diocese of Rockhampton CEO |
| 662 | St Mary's Catholic Primary School, NORTH ROCKHAMPTON | Diocese of Rockhampton CEO |
| 684 | St Patrick's Catholic Primary School, BUNDABERG WEST | Diocese of Rockhampton CEO |
| 680 | St Patrick's Catholic Primary School, EMERALD | Diocese of Rockhampton CEO |
| 17232 | St Patrick's College, MACKAY | Diocese of Rockhampton CEO |
| 5812 | St Paul's Catholic Primary School, GRACEMERE | Diocese of Rockhampton CEO |
| 693 | St Peter's Catholic Primary School, ROCKHAMPTON | Diocese of Rockhampton CEO |
| 709 | St Therese's Catholic Primary School, MONTO | Diocese of Rockhampton CEO |
| 726 | Star of the Sea Catholic Primary School, GLADSTONE | Diocese of Rockhampton CEO |
| 13654 | The Cathedral College, ROCKHAMPTON | Diocese of Rockhampton CEO |
| 17221 | Assumption College, WARWICK | Diocese of Toowoomba CSO |
| 17731 | Good Samaritan College, TOOWOOMBA | Diocese of Toowoomba CSO |
| 454 | Holy Name Primary School, TOOWOOMBA | Diocese of Toowoomba CSO |
| 17523 | Mary MacKillop Catholic College, HIGHFIELDS | Diocese of Toowoomba CSO |
| 478 | Mater Dei Primary School, TOOWOOMBA | Diocese of Toowoomba CSO |
| 498 | Our Lady of Lourdes Primary School, TOOWOOMBA | Diocese of Toowoomba CSO |
| 2248 | Our Lady of the Southern Cross College, DALBY | Diocese of Toowoomba CSO |
| 525 | Sacred Heart Primary School, CUNNAMULLA | Diocese of Toowoomba CSO |
| 528 | Sacred Heart Primary School, TOOWOOMBA | Diocese of Toowoomba CSO |
| 538 | St Anthony's School, TOOWOOMBA | Diocese of Toowoomba CSO |
| 565 | St Finbarr's School, QUILPIE | Diocese of Toowoomba CSO |
| 568 | St Francis De Sales School, CLIFTON | Diocese of Toowoomba CSO |
| 585 | St John's School, ROMA | Diocese of Toowoomba CSO |
| 17900 | St Joseph's College, TOOWOOMBA | Diocese of Toowoomba CSO |
| 598 | St Joseph's School, CHINCHILLA | Diocese of Toowoomba CSO |
| 622 | St Joseph's School, MILLMERRAN | Diocese of Toowoomba CSO |
| 5380 | St Joseph's School, STANTHORPE | Diocese of Toowoomba CSO |
| 629 | St Joseph's School, TARA | Diocese of Toowoomba CSO |
| 640 | St Maria Goretti School, INGLEWOOD | Diocese of Toowoomba CSO |
| 17229 | St Mary's College, TOOWOOMBA | Diocese of Toowoomba CSO |
| 2507 | St Mary's School, CHARLEVILLE | Diocese of Toowoomba CSO |
| 2149 | St Mary's School, GOONDIWINDI | Diocese of Toowoomba CSO |
| 660 | St Mary's School, WARWICK | Diocese of Toowoomba CSO |
| 668 | St Monica's School, OAKEY | Diocese of Toowoomba CSO |
| 676 | St Patrick's Primary School, MITCHELL | Diocese of Toowoomba CSO |
| 683 | St Patrick's School, ALLORA | Diocese of Toowoomba CSO |
| 686 | St Patrick's School, ST GEORGE | Diocese of Toowoomba CSO |
| 17237 | St Saviour's College, TOOWOOMBA | Diocese of Toowoomba CSO |
| 701 | St Saviour's Primary School, TOOWOOMBA | Diocese of Toowoomba CSO |
| 704 | St Stephen's School, PITTSWORTH | Diocese of Toowoomba CSO |
| 711 | St Thomas More's Primary School, TOOWOOMBA | Diocese of Toowoomba CSO |
| 17240 | Burdekin Catholic High School, AYR | Diocese of Townsville CEO |
| 17253 | Columba Catholic College, CHARTERS TOWERS | Diocese of Townsville CEO |
| 17227 | Gilroy Santa Maria College, INGHAM | Diocese of Townsville CEO |
| 17223 | Good Shepherd Catholic College, MOUNT ISA | Diocese of Townsville CEO |
| 14157 | Good Shepherd Catholic School, RASMUSSEN | Diocese of Townsville CEO |
| 2188 | Holy Spirit Catholic School, CRANBROOK | Diocese of Townsville CEO |
| 8770 | Marian Catholic School, CURRAJONG | Diocese of Townsville CEO |
| 467 | Our Lady of Lourdes Primary School, INGHAM | Diocese of Townsville CEO |
| 2529 | Ryan Catholic College, KIRWAN | Diocese of Townsville CEO |
| 15370 | Southern Cross Catholic College, ANNANDALE | Diocese of Townsville CEO |
| 77476 | St Anthony's Catholic College, DEERAGUN | Diocese of Townsville CEO |
| 30318 | St Benedict's Catholic School, SHAW | Diocese of Townsville CEO |
| 550 | St Catherine's Catholic College The Whitsundays, PROSERPINE | Diocese of Townsville CEO |
| 28618 | St Clare's Catholic School, BURDELL | Diocese of Townsville CEO |
| 553 | St Colman's School, HOME HILL | Diocese of Townsville CEO |
| 569 | St Francis Catholic School, HUGHENDEN | Diocese of Townsville CEO |
| 661 | St Francis' School, AYR | Diocese of Townsville CEO |
| 584 | St John Bosco Catholic School, COLLINSVILLE | Diocese of Townsville CEO |
| 617 | St Joseph's Catholic School, CLONCURRY | Diocese of Townsville CEO |
| 5353 | St Joseph's Catholic School, MOUNT ISA | Diocese of Townsville CEO |
| 624 | St Joseph's Catholic School, MUNDINGBURRA | Diocese of Townsville CEO |
| 605 | St Joseph's Catholic School, The Strand, NORTH WARD | Diocese of Townsville CEO |
| 5354 | St Kieran's Catholic School, MOUNT ISA | Diocese of Townsville CEO |
| 17225 | St Margaret Mary's College, HYDE PARK | Diocese of Townsville CEO |
| 649 | St Mary's Catholic School, BOWEN | Diocese of Townsville CEO |
| 666 | St Michael's Catholic School, PALM ISLAND | Diocese of Townsville CEO |
| 678 | St Patrick's Catholic School, WINTON | Diocese of Townsville CEO |
| 692 | St Peter's Catholic School, HALIFAX | Diocese of Townsville CEO |
| 17247 | St Teresa's College, ABERGOWRIE | Diocese of Townsville CEO |
| 25123 | Albert Park Flexible Learning Centre, MILTON | Edmund Rice Education Australia |
| 15656 | Ambrose Treacy College, INDOOROOPILLY | Edmund Rice Education Australia |
| 25125 | Deception Bay Flexible Learning Centre, DECEPTION BAY | Edmund Rice Education Australia |
| 29774 | Gympie Flexible Learning Centre, GYMPIE | Edmund Rice Education Australia |
| 29896 | Hemmant Flexible Learning Centre, HEMMANT | Edmund Rice Education Australia |
| 15655 | Ignatius Park College, CRANBROOK | Edmund Rice Education Australia |
| 30003 | Inala Flexible Learning Centre, INALA | Edmund Rice Education Australia |
| 29743 | Ipswich Flexible Learning Centre, IPSWICH | Edmund Rice Education Australia |
| 28895 | Mount Isa Flexible Learning Centre, SUNSET | Edmund Rice Education Australia |
| 25126 | Noosa Flexible Learning Centre, SUNSHINE BEACH | Edmund Rice Education Australia |
| 30209 | Rockhampton Flexible Learning Centre, ROCKHAMPTON | Edmund Rice Education Australia |
| 85178 | Southport Flexible Learning Centre, SOUTHPORT | Edmund Rice Education Australia |
| 15648 | St Brendan's College, YEPPOON | Edmund Rice Education Australia |
| 15649 | St Edmund's College, WOODEND | Edmund Rice Education Australia |
| 15650 | St James College, BRISBANE | Edmund Rice Education Australia |
| 15651 | St Joseph's College, BRISBANE | Edmund Rice Education Australia |
| 15652 | St Joseph's Nudgee College, BOONDALL | Edmund Rice Education Australia |
| 15653 | St Laurence's College, SOUTH BRISBANE | Edmund Rice Education Australia |
| 15654 | St Patrick's College, SHORNCLIFFE | Edmund Rice Education Australia |
| 17259 | The Centre Education Programme, KINGSTON | Edmund Rice Education Australia |
| 25124 | Townsville Flexible Learning Centre, WEST END - TOWNSVILLE | Edmund Rice Education Australia |
| 17217 | All Hallows' School, BRISBANE | Religious Institute |
| 17226 | Brigidine College, INDOOROOPILLY | Religious Institute |
| 17234 | Downlands College, TOOWOOMBA | Religious Institute |
| 17236 | Iona College, LINDUM | Religious Institute |
| 17238 | Loreto College Coorparoo, COORPAROO | Religious Institute |
| 17239 | Lourdes Hill College, HAWTHORNE | Religious Institute |
| 17241 | Marist College Ashgrove, ASHGROVE | Religious Institute |
| 17243 | Mount Alvernia College, KEDRON | Religious Institute |
| 17245 | Mt St Michael's College, ASHGROVE | Religious Institute |
| 17216 | Padua College, KEDRON | Religious Institute |
| 17233 | St Patrick's College Townsville, TOWNSVILLE | Religious Institute |
| 17235 | St Rita's College, CLAYFIELD | Religious Institute |
| 17248 | St Ursula's College, TOOWOOMBA | Religious Institute |
| 17249 | St Ursula's College, YEPPOON | Religious Institute |
| 17250 | Stuartholme School, TOOWONG | Religious Institute |
| 17251 | Villanova College, COORPAROO | Religious Institute |